## Sheet2
PHASE/ACTIVITY | TIMELINE
| 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01
SEMESTER 1 | bar: 2026-10-01 to 2026-12-01
Phase 1: Project Definition and literature | bar: 2026-10-01
Literature review and business problem | bar: 2026-10-01
Define research question, aim and objectives | bar: 2026-10-01
Phase 2: Data Acquisition and Processing | bar: 2026-10-01 to 2026-12-01
Identify data sources and access | bar: 2026-10-01
Data collection | bar: 2026-11-01 to 2026-12-01
Data cleaning and integration | bar: 2026-12-01; 2027-02-01
Exploratory data analysis (EDA) | bar: 2027-02-01
SEMESTER 2 | bar: 2027-02-01 to 2027-06-01
Phase 3: Predictive Modeling and Evaluation | bar: 2027-02-01 to 2027-03-01
Predictive model development | bar: 2027-02-01 to 2027-03-01
Model evaluation and interpretation | bar: 2027-03-01
Milestone 1: Analytical Dataset, predictive model and evaluation Completed
Phase 4: Scenario Analysis and Insights | bar: 2027-03-01
Scenario analysis | bar: 2027-03-01
Strategic sustainability insights | bar: 2027-03-01
Phase 5: Reporting and Final Submission | bar: 2027-03-01
Final report writing and formatting | bar: 2027-03-01
Milestone 2: Final Report Submission